## Design Parameters
Customer | P-25 |  |  | Estimate Prepared
Engineer | MARK PROKOP |  |  | By
Project Name | FVTX ROC Proto PCB |  |  | Tom and Stacy
Designer Name | TBD |  |  | 2009-12-03
# New Schematic Symbols | 0 |  |  | Cost
small (< 4 pins) | 0 |  |  | Total Billable Hours | 847.775
medium (< 44 pins) | 0 |  |  | Hourly Rate | 0
Large (< 144 pins) | 0 |  |  | Add on % | 0%
XLarge (< 384 pins) | 0 |  |  | Cost Adders | 0
XXLarge (< 672 pins) | 0
Huge (> 672 pins) | 0 |  |  | Total Design Cost | 0
# New PDB Entries | 0
small (< 4 pins) | 0
medium (< 44 pins) | 0
Large (< 144 pins) | 0
XLarge (< 384 pins) | 0
XXLarge (< 672 pins) | 0
Huge (> 672 pins) | 0
# of New Footprints (cells) | 0
small (< 4 pins) | 0
medium (< 35 pins) | 0
large (>35pins) | 0
# Schematic Sheets | 0
D Size simple | 0
D Size moderate | 0
D Size complex | 0
Board Width (inches)* | 10.89
Board Height (inches)* | 9.88
#Layers | 20 |  |  | Schedule
|  |  |  | ECAD hours | 847.775
# PCB Constraints (slots, holes, keepouts) | 1 | gas seal |  | Customer hours | 64
|  |  |  | Total Schedule Hours* | 911.775
total # of parts in design | 3005 |  |  | * includes customer review time and ECAD design time
# constrained parts (fixed connectors, etc) | 75
# unconstrained parts | 2180
# replicated parts | 750 |  |  | Hours per Day | 8
|  |  |  | Days per Week* | 5
total # Nets in design | 3595
# Differential pairs (total diff nets / 2) | 967
#Controlled Impedance nets | 32
# tuned nets | 546
# autorouted nets | 684
# handrouted nets (Clocks, etc.) | 34 |  | Handroute | Start Date | 2009-12-08
PWR/GND Plane Shapes and Traces | 365 |  |  | Est End Date | 2010-05-16 13:27

## time factors
Designer | TBD
Customer | P-25
Project | FVTX ROC Proto PCB
Engineer | MARK PROKOP | Billable Hours |  |  | Schedule Hours |  | Total
| Design Step | Constant | Dependent | Total | Customer Wait | Total | Billable (hours) | Schedule (hours) | Weeks
Design Kickoff | Define Project Scope | 1 |  | 1 |  | 1 | 1.5 | 9.5 | 0.2375
| Define Schedule | 0.5 |  | 0.5 |  | 0.5 |  |  |  | Total Billable | 847.775
| Customer Signoff |  |  | 0 | 4 | 4
| Wait for Required Inputs |  |  | 0 | 4 | 4 |  |  |  | Total Schedule | 911.775
| Extra Kickoff Time |  |  | 0 |  | 0
Schematic Entry | Create New Project File | 0.25 |  | 0.25 |  | 0.25 | 4.25 | 12.25 | 0.30625 | Total Sched Weeks | 22.7944
| Research Parts | 2 |  | 2 |  | 2
Create New Schematic Symbols
| Small |  | 0 | 0 |  | 0
| Medium |  | 0 | 0 |  | 0
| Large |  | 0 | 0 |  | 0
| XLarge |  | 0 | 0 |  | 0
| XXLarge |  | 0 | 0 |  | 0
| Huge |  | 0 | 0 |  | 0
Create New PDB entries
| Small |  | 0 | 0 |  | 0
| Medium |  | 0 | 0 |  | 0
| Large |  | 0 | 0 |  | 0
| XLarge |  | 0 | 0 |  | 0
| XXLarge |  | 0 | 0 |  | 0
| Huge |  | 0 | 0 |  | 0
Capture Schematic
| Simple |  | 0 | 0 |  | 0
| Moderate |  | 0 | 0 |  | 0
| Complex |  | 0 | 0 |  | 0
| Customer Review/Signoff | 2 |  | 2 | 8 | 10
PCB Setup | Build Board Outline | 1 |  | 1 |  | 1 | 1.3 | 1.3 | 0.0325
| Convert Netlist | 0 |  | 0 |  | 0
Build Component Cells
| small |  | 0 | 0 |  | 0
| medium |  | 0 | 0 |  | 0
| large |  | 0 | 0 |  | 0
| Define Design Constraints |  | 0.3 | 0.3 |  | 0.3
| Extra Setup Time |  |  | 0 |  | 0
Parts Placement | Critical Placement |  | 18.75 | 18.75 |  | 18.75 | 196.15 | 212.15 | 5.3037
| Critical Review & Signoff | 1 |  | 1 | 8 | 9
| General Placement |  | 174.4 | 174.4 |  | 174.4
| General Review & Signoff | 2 |  | 2 | 8 | 10
| Extra Placement Time |  |  | 0 |  | 0
Routing | Critical Routing | [5 empty] | 488.6 | 504.6 | 12.615
| Differential pairs |  | 241.75 | 241.75 |  | 241.75
| Tuned + Controlled Impd. |  | 115.6 | 115.6 |  | 115.6
| Critical Review & Signoff | 1 |  | 1 | 8 | 9
| Autorouting |  | 68.4 | 68.4 |  | 68.4
| Handrouting |  | 59.85 | 59.85 |  | 59.85
| Routing Review & Signoff | 2 |  | 2 | 8 | 10
| Extra Routing Time |  |  | 0 |  | 0
Manufacturing | Silkscreen | 1 | 45.1 | 46.1 |  | 46.1 | 154.975 | 162.975 | 4.0744
| Pastemask | 1 |  | 1 |  | 1
| Soldermask | 1 |  | 1 |  | 1
| Fab Drawings | 4 | 4 | 8 |  | 8
| Generate Outputs | 4 |  | 4 |  | 4
| DRC's | 4 | 89.875 | 93.875 |  | 93.875
| Manufacturing Review & Signoff | 1 |  | 1 | 8 | 9
| Extra Manufacturing Time |  |  | 0 |  | 0
Customer Acceptance | Final Signoff | 1 |  | 1 | 8 | 9 | 1 | 9 | 0.225

## Time_Log
Date | Name | Task Description | Hours (minimum=.25) | code | Estimated ECAD Hours | 847.775
2009-12-11 | CHACON | UPDATED SCHEMATIC SHEETS (57-62) | 2.5 | ZD05 5000 0000 | ECAD Hours Logged | 279
2009-12-11 | CHACON | ADDED GLOBALS TO LIST | 1 |  | Balance | 568.775
2009-12-14 | CHACON | ADDED GLOBALS TO LIST | 2 |  | FVTX ROC PCB
2009-12-14 | CHACON | UPDATED SCH (19,20,26,27,33,34,40,41) | 4
2009-12-14 | CHACON | MET WITH MARK TO FIX INTERCONNECT ERRORS | 1 |  | Est. Customer hours | 64
2009-12-14 | CHACON | STARTED DEFINING DIFF PAIRS (1-214) | 1 |  | Customer hours used
2009-12-17 | CHACON | DEFINING DIFF PAIRS (215-741) | 2.5 |  | Customer hours balance | 64
2009-12-17 | CHACON | DEFINING DIFF PAIRS (742-979) | 1
2009-12-17 | CHACON | PLACE PARTS - WEDGES | 1
2009-12-17 | CHACON | PRELIMINARY LAYER STACKUP | 1
2009-12-17 | CHACON | DEFINED TUNED NETS (MATCH # AND TOLERANCE) | 1
2009-12-17 | CHACON | UPDATED SCHS(INTERCONNECT ERRORS (130 DOWN TO 23) | 1.5
2010-01-05 | CHACON | WORKED W/ MARK TO FINISH INTERCONNECT ERRORS | 2
2010-01-05 | CHACON | PACKAGED DESIGN (GLOBAL/REF DES ERRORS~130) | 3 |  | Project hours balance | 632.775
2010-01-05 | CHACON | MISC SCHEMATIC UPDATES | 2
2010-01-05 | CHACON | STARTED PLACING PARTS WEDGE0 POWER SUPPLIES | 2
2010-01-07 | CHACON | COPIED CIRCUITS FROM WEDGE 0, SHOVED PARTS | 3
2010-01-12 | CHACON | PLACED PRELIMINARY CIRCUITRY FOR WEDGE 1, 2, 3 | 3
2010-01-12 | CHACON | GENERATED PDF PRINTS OF SCHEMATIC SET | 0.5
2010-01-12 | CHACON | GENERATED PDF OF PRELIMINARY PARTS PLACEMENT | 0.5
2010-01-12 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-01-25 | COTE | Design Rules/Diff Pair swapping rules | 12
2010-01-26 | CHACON | GENERATED/UPDATED BOM | 2
2010-02-01 | COTE | Refined Design Rules/Diff Pair swapping rules | 5
2010-02-02 | CHACON | CONTINUED PLACING PARTS | 7.5
2010-02-04 | CHACON | CONTINUED PLACING PARTS | 3
2010-02-04 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-02-08 | COTE | Evaluated CES, Fixed pin pair mis-matches in A3PE3000 symbols | 7
2010-02-09 | CHACON | PLACED ALL MAJOR COMPONENTS | 1
2010-02-09 | CHACON | MET WITH MARK AND TOM TO DISCUSS PLACEMENT ISSUES | 1.5
2010-02-09 | CHACON | MOVED TRANSCIEVERS (TLK7211) CLOSER TO BGAs | 1
2010-02-09 | CHACON | MOVED RECEIVERS (MAX 9113) AND THEIR CIRCUITRY | 0.5
2010-02-11 | CHACON | UPDATED BOM WITH HEIGHT SPECIFICATIONS | 3
2010-02-11 | CHACON | WORKED WITH TOM AND MARK UPDATING NEW FPGA SYBMOLS | 1
2010-02-11 | CHACON | SAVED LATEST VERSION IN P-25 MAILBOX FOR REVIEW | 0.5
2010-02-16 | CHACON | MOVED CLOCK DISTRIBUTION CIRCUITRY | 1.5
2010-02-16 | CHACON | MOVED BCO AND START CLOCK CIRCUITRY | 1
2010-02-16 | CHACON | REVIEWED LAYER STACK-UP AND IMPEDANCE CALCULATION | 1.5
2010-02-16 | CHACON | FANNED OUT DF18C CONNECTOR | 1.5
2010-02-16 | CHACON | STARTED MOVING/ROUTING INPUT TERMINATIONS (DF18C) | 1.5
2010-02-18 | CHACON | CONTINUED MOVING/ROUTING INPUT TERMAINATIONS | 4
2010-02-18 | CHACON | MET WITH MARK AND TOM TO REVIEW LAYOUT | 2
2010-02-18 | CHACON | PLACED LATEST VERSION IN P-25 MAILBOX FOR REVIEW | 0.5
2010-02-18 | COTE | 1st Evaluation autoroute of diff pairs, meet with Mark and Stacy | 9
2010-02-22 | COTE | Evaluated new fan-outs, autorouted diff pairs in horizontal wedge | 15
2010-02-23 | CHACON | DELETED TERMINATING RESISTORS | 1
2010-02-23 | CHACON | MODIFIED FORCED ROUTE ORDER (TERM RESISTORS) | 3.5
2010-02-23 | CHACON | MET WITH TOM TO DISCUSS FANOUT OPTIONS | 1
2010-02-23 | CHACON | FANNED OUT WEDGE CONNECTORS USING NEW SCHEME | 2.5
2010-02-25 | CHACON | COPIED TOM's VERSION WITH DIFF PAIR ROUTING | 0.5
2010-02-25 | CHACON | PLAYED WITH CIRCUIT MOVE/ROTATE | 1
2010-02-25 | CHACON | Met with Tom and Mark and worked through copy/rotate problems | 2
2010-02-25 | CHACON | CONTINUED WORKING WITH MOVE/COPY/ROTATE CIRCUIT | 3
2020-03-02 | CHACON | CONTINUED WORKING WITH MOVE/COPY/ROTATE CIRCUIT | 1
2010-03-06 | COTE | Extended board outline, added mounting holes, met with Mark | 9
2010-03-11 | CHACON | SET UP BGA_1MM RULE AREA | 0.5
2010-03-11 | CHACON | PLACED DECOUPLING CAPS (pgs. 14,15,16,17,18,45) | 6.5
2010-03-16 | CHACON | PLACED DECOUPLING CAPS (pgs. 19,20,43,44,45) | 6.5
2010-03-16 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-03-23 | CHACON | UPDATED TIME LOG | 0.5
2010-03-23 | CHACON | CONTINUED PLACING PARTS | 4.5
2010-03-23 | CHACON | MET WITH MARK-COMPONENT (CONNECTOR) PLACEMENT | 0.5
2010-03-26 | CHACON | CONTINUED PLACING PARTS | 8
2010-03-30 | CHACON | CONTINUED PLACING PARTS | 6
2010-04-01 | CHACON | CONTINUED PLACING PARTS | 2.5
2010-04-06 | CHACON | CONTINUED PLACING PARTS | 6
2010-04-08 | CHACON | CONTINUED PLACING PARTS | 7
2010-04-13 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-04-13 | CHACON | MET WITH MARK TO DISCUSS CONNECTOR CHANGES | 0.5
2010-04-13 | CHACON | MET WITH TOM TO DISCUSS SCHEMATIC/LAYOUT CHANGES | 0.5
2010-04-13 | CHACON | SCHEMATIC CHANGES - MIRROR CONNECTORS | 7
2010-04-15 | CHACON | ROTATED PARTS DUE TO CONNECTOR CHANGES | 5
2010-04-15 | CHACON | GOT COMPUTER/FILES READY TO TAKE HOME | 1.5
2010-04-16 | CHACON | COMPUTER SET UP AT HOME | 1.5
2010-04-16 | CHACON | AUTOROUTED DIFF PAIR LAYERS | 3.5
2010-04-18 | CHACON | ADDED PLANES/BLIND VIAS | 1.5
2010-04-18 | CHACON | AUTOROUTED DIFF PAIR LAYERS | 3.5
2010-04-20 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-04-30 | CHACON | RESET PARTS/BLIND VIAS/ COMPILED LIST OF GND PINS | 5
2010-05-02 | CHACON | RESET CLEARANCES | 1
2010-05-02 | CHACON | STARTED MANUALLY ROUTING DIFF PAIRS | 3
2010-05-02 | CHACON | STARTED LOOKING AT GATE SWAPPING | 1
2010-05-07 | CHACON | ROUTED DIFF PAIRS - LAYER 3 | 5
2010-05-11 | CHACON | STARTED SWAPPING DIFF PAIRS - LAYER 3 | 3
2010-05-11 | CHACON | REVIEWED BGA GUIDELINES | 1.5
2010-05-11 | CHACON | ESCAPE ROUTING - LAYER 3 | 3.5
2010-05-14 | CHACON | SENT MELYNDA UPDATE | 0.5
2010-05-14 | CHACON | DIFF PAIR ROUTING - LAYER 3 | 7.5
2010-05-15 | CHACON | DIFF PAIR ROUTING - LAYER 5 | 5
2010-05-18 | CHACON | SWAP DIFF PAIRS | 2
2010-05-18 | CHACON | DIFF PAIR ROUTING - LAYER 5 | 6
2010-05-20 | CHACON | REROUTED DIFF PAIRS LAYER 5 - W/IN SAME SWAP GROUP | 7
2010-05-21 | CHACON | REROUTED DIFF PAIRS LAYER 5 | 5
2010-05-23 | CHACON | DIFF PAIR ROUTING - LAYERS 3 AND 5 | 5